## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 89 | 0 |  |  |  | 21 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0
| 2017-02-01 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Wed | Fri | Sun | Wed | Fri | Sun | Wed | Fri | Sun | Wed | Wed | Wed | Wed | Wed | Wed | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2017-01-11 | 2017-01-13 | 2017-01-15 | 2017-01-18 | 2017-01-20 | 2017-01-22 | 2017-01-25 | 2017-01-27 | 2017-01-29 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
5 |  | ——Preparation—— | [23 empty] | Assigned
6 | 1 | Play / study original zelda game | All |  | 2 |  |  |  | 2 | 2017-01-11: 1; 2017-01-13: 0 | Google search "zelda nes online" and you should figure out how to easily play the game. Otherwise, visit the videogame archive in the basement of the Duderstadt. | Active
7 | 1 | Watch zelda tutorial (canvas) | All |  | 2 |  |  |  | 2 | 2017-01-11: 1; 2017-01-13: 0 | There are two Zelda tutorials available for viewing. Read how they're different in the Piazza template repo. | Verify?
8 | 2 | Mess With 494 Quest | All |  | 2 | 0 |  |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494 Quest was built for you to examine, pilfer, and learn from. | Fixed
9 | [25 empty] | Deferred
10 | [25 empty] | Fact of Life
11 | [25 empty] | Can't Repro
12
13
14
15 |  | ——Player Character——
16 | 1 | Grid-based movement | NEB |  | 4 | 0 |  |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 1 | Health and damage cooldown (damage-invincibility) | CB |  | 2 | 0 |  |  | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A nasty side-effect of not implementing a damage cooldown or "vulnerability-period" is that players die exceedingly quickly.
18 | 3 | HUD and Item Selection Capability (item menu). | CB |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Building menus and simple inventory management systems is necessary in many games, and good experience to get. Be thankful you're not making Pokemon, like the F15 class did.
19 | 2 | Collectable Pickup Capability (Hearts, rupees, items) | CB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 3 | Bow Weapon Functionality | NEB |  | 3 |  |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 0
21 | 3 | Boomerang Weapon Functionality | NEB |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The boomerang has many functionalities-- be sure to implement them all!
22 | 3 | Shield, Reflect Projectiles | NEB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 2 | Bomb Weapon Functionality | NEB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 2 | Sword Functionality | NEB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 3 | Character animation | NEB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 |  | Beam Sword | NEB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28
29
30
31
32
33
34
35 |  | ——Enemies——
36 | 1 | Stalfos - Skeleton Enemies | All |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 2 | Keese - Bat Enemies | All |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 2 | Goriya - Boomerang Enemies | NEB |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 3 | Bladetrap - Spike Obstacle Enemies | NEB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 2 | Gel - Slow Enemies | NEB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 3 | Wallmaster - Creepy Hand Enemies | NEB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The wallmaster reset's Link's position in the dungeon, but not the dungeon itself! Don't be lazy and just call Application.LoadLevel()!
42 | 2 | Aquamentus - Dragon Boss | NEB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 2 | Make enemies stay in room environments | NEB |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44
45
46
47
48
49
50 |  | ——Environment——
51 | 1 | Room Transitions | NEB |  | 3 | 0 |  |  | 3 | 3 | 3 | 2.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 1 | Locked Doors | CB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 2 | Pushable Blocks | CB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 3 | Old-Man Room (Simple Speech Engine) | NEB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Speech and dialogue engines appear in many games, often as the primary driver of plot and character development. Zelda's dialogue system is simple, and provides an opportunity for experience.
55 | 3 | 2D Room (Bow Room) | NEB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
56 | 2 | Water tiles (allow projectiles but not physical entities) | NEB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57
58
59
60
61
62 |  | ——Custom Level Stuff Goes Here——
63 | 4 | Sound Effects | All |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0
64 | 2 | Moving block enemy prefab | CB |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
65 | 2 | Running block prefab | CB |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0
66 | 1 | make custom map text file | CB |  | 6 | 0 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 3 | Creepy music track? | CB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
68 | 2 | new block art (blocked door, target tile, block mobs) | CB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 1 | pickaxe functionality | NEB |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 3 | Mob placement | CB |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 4 | make running blocks hurt boss | CB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
72 | 2 | unlock triforce door when boss is killed | CB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 4 | make pickaxe room a safe maze | CB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
74 | 3 | animate block mobs with proximity to player | CB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
75 |  | alive block projectile interactions | NEB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
76 |  | Custom Level Boss | All |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 | [25 empty] | Reported
108 | [25 empty] | Reported
109 | [25 empty] | Reported
110 | [25 empty] | Reported
111 | [25 empty] | Reported
112 | [25 empty] | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 21 | 21 | 19 | 17 | 14 | 12 | 10 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0
211 |  | Optimum | [5 empty] | Line | 89 | 89 | 80.5238 | 72.0476 | 59.3333 | 50.8571 | 42.381 | 29.6667 | 21.1905 | 12.7143 | 0 | 0 | 0 | 0 | 0 | 0
212
213 |  | Sum | [6 empty] | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 21 | 22 | 16 | 14.5 | 13 | 10 | 9 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 |  |  | 2 | [5 empty] | 31 | 30 | 29 | 29 | 29 | 22 | 19 | 10 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0
217 |  |  | 3 | [5 empty] | 28 | 28 | 28 | 28 | 28 | 25.5 | 23.5 | 15 | 13 | 5 | 0 | 0 | 0 | 0 | 0 | 0
218 |  |  | 4 | [5 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Neil Banchero-Smith | NEB |  |  |  |  | NEB | 43 | 46 | 43 | 42.5 | 42 | 34 | 29 | 13 | 11 | 4 | 0 | 0 | 0 | 0 | 0 | 0
223 |  | Chris Boston | CB |  |  |  |  | CB | 33 | 33 | 32 | 31 | 31 | 29.5 | 28.5 | 19 | 19 | 9 | 0 | 0 | 0 | 0 | 0 | 0
224 |  | All | All |  |  |  |  | All | 16 | 13 | 10 | 10 | 9 | 6 | 6 | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0
225 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89
236

## Daily Scrum
Producer | 2017-02-01 |  | Team Members
Approved | Dates |  | Neil Banchero-Smith | Chris Boston | All
| 2017-01-11 | Wed | Done: Talked about level design Next: Can't work tomorrow Help: Shield Functionality | Done: similar game research Next: write paper Help: -- | Done: Took exam Next: Catch up, figure out what to do Help: Need to talk with everyone
| 2017-01-13 | Fri | Done: Research Paper, Worked on 485 project Next: Movement Help: Shield + Boomerang Interaction questions | Done: research paper Next: implement player health and damage Help: player state? | Done: Caught up. Set up GIT Next: Prototype enemies Help: —
|  | Sat | Done: Grid Movement (SO SUBTLE but complicated)+ Links hitbox. Movement is 1:1 to NES game now Next: Level Transitions + Hud + Editing Research Paper + 485 Project Help: Burntout (Grid movement took around 6 frustrating hours), might not get a lot done today | Done: worked on 484 project, player health Next: implement damage function | Done: Movement Next: Enemies and player interaction Next: Editing research paper and final touches
| 2017-01-18 | Wed | Done: 485 Project, some inital level movement research Next: Level Transitions + Hud. Heavy Catchup Help: Statemachines | Done: Parts of Playerhealth, Utlites, and godmode Next: Player collision damage & enemies Help: AI movement? | Done: Look at invidual Next: Push to catchup to goals, prepare Alpha Help: Statemachine implementation
| 2017-01-20 | Fri | Done: 485 Project, tuning of movement, reading up on Camera Next: Camera/Level Movement, Sword, Rupees, Animation Help: Some Camera stuff ( | Done: Player collision, Basic enemy (stalfos) prefab. Next: Bat enemies Help: How do I make enemies spawn/despawn with camera? | Done: Player Collision, Basic Prepfabs for enemies
| 2017-01-22 | Sun | Done: Sword + Stalfos Fixes + Entire Level is mapped out Next: Boomerang, Bomb Help: State Machine for other enemies? Projectile Bouncing on Shield | Done: 484 project, 481 project, Bat enemies, locking doors Next: pushable blocks, items reflected in UI Help: flying bats | All : HUD is important
| 2017-01-25 | Wed | Done: Kesse, Goriya, Bombs, Boomerang, FInal Boss, Bladetraps, Gels, Shield, BeamSword, Keeping enemies in room constraints, item drops, Visual cues for enemies both attacks and death, restart level, and placed all enemies and items in the dunegon Next: Bow + BowRoom, Wallmaster Help: Wallmaster | Done: pushable blocks, basic UI functionality, item pickup +item prefabs, fixed double pickup glitch, fixed door locking glitch, created new custom map, added environments to new custom map Next: custom mobs and blocks Help: new boss? | All: Custom Level Sketch Next: Finish Classic then move onto Custom Level
| 2017-01-27 | Fri | Done: Player Tweaks, Enemy Placement and AI changes, eecs 485 project Next: Bow Room, Old Man, Wallmaster | Done: Map design finished, began mob placement Next: new block prefabs | Next: AI bugs and Weapon interactions, coding new level weapons and layout
| 2017-01-29 | Sun | Done: Bow, Wallmaster Starter Next: Bow Room, Old Man Unlock, Finish Wallmaster, fix Custom Level enemies Help: Some wallmaster rotues | Done: mob placement, custom map sprites for new prefabs, final door mechanics Next: Finish block prefabs Help: Pickaxe | next: Cheats + Proper Inputs as in the Spec Help: Block Enemy reactions, fixing up code for the custom level
| 2017-02-01 | Wed
| 2017-02-01 | Wed
| 2017-02-01 | Wed
| 2017-02-01 | Wed
| 2017-02-01 | Wed
| 2017-02-01 | Wed